## Dashboard
SKAAH Hospitality Website: Independent QA and Audit Execution Workbook
Baseline: SoW v1.3 s13 and spec docs 01-09. Fill only the shaded columns on each sheet (Result, Evidence link, Tester, Date, Notes). Result uses the dropdown. Evidence rule: no evidence, no pass; store proof under /QA-Evidence/<sheet-id>/.
Severity if fail: C = Critical (blocks launch), M = Major (blocks launch), Mn = Minor (may launch only when logged with owner and a 30 day fix date; CEO approval, CTO sign-off).
Example of a completed row (format to follow):
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
FE-09 | 100 MB upload on 4G | Uploaded 98 MB PDF, throttled 4G, Android | Succeeded with progress; file in payload | SoW 8.1 | C | Pass | /QA-Evidence/FE-09/ | R. Meegada | 2026-09-14 | Retested after fix 1x
Progress summary (live formulas)
Sheet | Total | Pass | Fail | Blocked | N.A. | Open | Critical fails | Major fails
1-Code-Audit
2-Content-Claims
3-Functional-Enquiry
4-SEO-Schema
5-Performance
6-Accessibility
7-Security-Residency
8-Compat-Matrix
9-CMS-Editorial
10-Deploy-Ops
TOTAL
Launch readiness

## 1-Code-Audit
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
CA-01 | Repo structure matches spec | Fresh clone; compare folders and routes to docs/04 s6 and docs/01 s3 | Structure matches; any deviation has a DECISION comment | 04 s6 | M | Pass | QA-Evidence/CA-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest after fix: e2e/ scaffold added (playwright.config.ts, e2e/smoke.spec.ts, pnpm test:e2e per CLAUDE.md E0); suite runs green (4 passed) against the production build. All other structural deviations were already documented. Original finding stands as fixed.
CA-02 | TypeScript strict, clean typecheck | Inspect tsconfig; run pnpm typecheck | strict true; zero errors | 04 s6 | M | Pass | QA-Evidence/CA-02/ | Claude Code (automated pre-audit) | 2026-08-21 | tsconfig has strict:true plus noUncheckedIndexedAccess; npx tsc --noEmit (TS 5.9.3) exits 0 with zero errors. Note: tsconfig excludes scripts/ from the typecheck scope.
CA-03 | Design tokens exact | Diff Tailwind theme values against docs/04 s1 | All values exact incl. 164069 blue, greens, golds | 04 s1 | M | Pass | QA-Evidence/CA-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Programmatic diff of app/globals.css @theme vs docs/04 s1: all 17 colours (incl. #164069 navy-900, greens #175A43/#1E6E52, golds #BFA05A/#9A7B2D), radii, container widths, gutter and shadow-card exact (hex case differs only). Font tokens reference var(--font-cormorant)/var(--font-inter) from self-hosted next/font/local instead of literal family names: functional equivalent that satisfies the self-hosted font requirement.
CA-04 | No hardcoded colours | Search hex values outside token definitions | None, or documented exceptions only | 04 s6 | Mn | Pass | QA-Evidence/CA-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: HeroFilm literal replaced with color-mix(in srgb, var(--color-gold-500) 14%, transparent); zero undocumented colour literals remain (the staging-only amber badge in Copy.tsx stays documented in code).
CA-05 | Component inventory C01-C29 present | List components dir; map to inventory | All 29 exist with specified names | 04 s3 | M | Pass | QA-Evidence/CA-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: C23 FilmBlock built (click-to-play, poster-first, provider-pending DECISION), C26 LangSwitcher built and mounted (renders only when routing.locales exceeds 1, per spec built-but-hidden), C29 NoticeBar built (global-toggled, disabled by default). Full C01-C29 inventory now present with accepted equivalents.
CA-06 | Server components by default | Audit use client directives | Only the listed interactive components are client | 04 s6 | Mn | Pass | QA-Evidence/CA-06/ | Claude Code (automated pre-audit) | 2026-08-21 | 16 use-client files. 6 are on the docs/04 s6 list (C15, C17 x2, C18, C24, header menus). 10 extras all justified: error.tsx (Next.js framework requirement), CookiePreferences (C24 consent surface), HubNav/WorkFilters (interactivity the docs/04 s4 templates require; grid stays server-rendered), and 5 analytics wrappers (BudgetBandTable, HubTimeline, CaseStudyMetaRow with DECISION comment, PartnerCta, WhatsAppLink) forced by docs/06 s7 event wiring, plus lib/analytics.ts. No static content component is client; C03 HeroFilm and C22 GalleryScroller are stricter (server) than the spec allows. Judged Pass: docs/04 list predates event wiring; every extra carries an in-code rationale.
CA-07 | Secrets scan clean | Run gitleaks over full git history | Zero findings | 05 s6 | C | Pass | QA-Evidence/CA-07/ | Claude Code (automated pre-audit) | 2026-08-21 | gitleaks detect over full history (7 commits, ~783 KB scanned): no leaks found, exit 0, empty findings report archived.
CA-08 | Dependency vulnerabilities | Run pnpm audit for production deps | No critical or high advisories open | 05 s6 | M | Pass | QA-Evidence/CA-08/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: pnpm overrides pin postcss ^8.5.6 and sharp ^0.35.3 over next 15.5.23 transitive pins (Next kept at 15 per docs/05). pnpm audit --prod: No known vulnerabilities found. Build, tests and e2e green.
CA-09 | Licence compliance | Generate dependency licence report | No conflicting copyleft; report archived | SoW 9.2 | Mn | Pass | QA-Evidence/CA-09/ | Claude Code (automated pre-audit) | 2026-08-21 | pnpm licenses list --prod archived (JSON + summary). Mix is MIT/Apache-2.0/ISC/BSD/0BSD/MIT-0/CC-BY-4.0 plus one LGPL-3.0-or-later: @img/sharp-libvips-linux-x64 (standard dynamically linked libvips prebuild, server-side only, not distributed to clients). Weak copyleft, no GPL/AGPL: no conflicting copyleft for this use.
CA-10 | Claims gate passes and actually bites | Run pnpm check:claims on prod build; then seed a long dash and a forbidden phrase in a branch and run again | Clean build passes; seeded branch fails the gate | CLAUDE.md | C | Pass | QA-Evidence/CA-10/ | Claude Code (automated pre-audit) | 2026-08-21 | Clean run exits 0. On temp branch qa/ca10-seed, one line seeded into content/home.ts with an em dash + 'international organisations' + 'WEF Davos': gate exits 1 with exactly 3 findings, one per class, incl. the restricted-WEF-wording rule from the approved amendment (content/disclaimer.ts sole allowed location). Checkout restored to clean 8b6e82d. Deviation noted: script scans source trees, not 'build output' as docs/07 T0.4 words it (equivalent coverage for the current typed content layer).
CA-11 | Zero TO CONFIRM in build output | Run claims gate; grep build output | None present | 01 s6 | C | Fail | QA-Evidence/CA-11/ | Claude Code (automated pre-audit) | 2026-08-21 | node scripts/check-claims.mjs --production: exits 1 with 78 unresolved [TO CONFIRM markers across content/, messages and lib/site.ts; production builds are correctly blocked (build:production runs this gate first). Fail records the designed pre-launch state per workbook instruction: markers await client facts (mailboxes, WhatsApp/phone, LinkedIn, venue lists, approved disclaimer wording); the gate itself works as specified. Round 2: count reduced to the facts genuinely awaiting the client (metadata trims resolved none of these by design).
CA-12 | export:content proven | Run pnpm export:content; open archive | Complete JSON plus media; procedure documented | SoW 9.2 | C | Pass | QA-Evidence/CA-12/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: export imports content/davos-week directly (stale davos-wef import removed, silent catch removed so a missing module fails loudly) and now exports globals.json and disclaimer.json. Archive verified complete: 9 JSON files plus brand media.
CA-13 | Seed content fidelity | Diff CMS seed for 3 sample pages vs docs/02 | Copy matches source of truth | 02 | M | Pass | QA-Evidence/CA-13/ | Claude Code (automated pre-audit) | 2026-08-21 | Rendered text of /en, /en/services/government-delegations and /en/destinations/zurich captured and compared line-by-line to docs/02.01, 02.02 B and 02.04. Copy verbatim incl. meta titles, all section orders, stat cards, 8 capability cards, 5 FAQs, Zurich sample day; every divergence is either the approved 21 Aug 2026 change (Davos Week vocabulary, /davos-week CTA, fallback proof line, footer disclaimer with its [TO CONFIRM] wording marker) or a spec [TO CONFIRM] marker rendered with the staging badge. Minor observation: Zurich venue-archetype capacity ranges are generic figures not sourced from docs/02 (named venues correctly held behind the marker).
CA-14 | .env.example complete | Compare keys to docs/07 env list | All keys present, no real values | 07 | Mn | Pass | QA-Evidence/CA-14/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: DATABASE_URL, PAYLOAD_SECRET and S3_ENDPOINT/BUCKET/KEY/SECRET added as reserved keys with epic annotations; every docs/07 key now present, no real values.
CA-15 | Commit hygiene | Sample 20 commits | Task IDs per docs/07; reviewable sizes | 07 | Mn | Fail | QA-Evidence/CA-15/ | Claude Code (automated pre-audit) | 2026-08-21 | git log with per-commit shortstat, all 7 commits sampled (100%). Messages are clear and mostly ID-prefixed, but at epic level (T0, T1-T3, T3, T4), not the per-task T3.4-style IDs docs/07/CLAUDE.md prescribe, and two commits bundle entire epics (75 files/6,225 insertions; 35 files/3,875 insertions): not 'commit-sized tasks' or reviewable sizes. Spec-import and trademark-amendment commits are well scoped.
CA-16 | S0 FreeBSD evidence | Read docs/decisions/S0.md and server build log | sharp and better-sqlite3 built on the Flex server | 08 s7 | C | Blocked | QA-Evidence/CA-16/ | Claude Code (automated pre-audit) | 2026-08-21 | Blocked pre-staging: spike S0 must run on the Hostpoint Flex (FreeBSD) server, which does not exist yet; no SSH target available. Programmatic pre-check filed: docs/decisions/S0.md absent (docs/decisions/ dir does not exist), no server build log in repo; S0 is referenced in docs/07 T0.8, docs/08 s7 and deploy-staging.yml but unexecuted.

## 2-Content-Claims
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
CC-01 | 27-page copy fidelity | Open each of the 27 pages; compare H1, hero, key sections to docs/02 | Matches or has an approved change log entry | 02 | M | Pass | QA-Evidence/CC-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Method: crawled all 36 /en routes, parsed rendered H1/H2 (python html.parser, not Screaming Frog — deviation), compared to docs/02-content. 27/27 pages match spec H1s byte-identically; only divergences are approved-change-log WEF replacements (CS2 title 'A first-time state delegation at Davos Week' + slug, insight title 'The 180-Day Davos Delegation Countdown', hub route /davos-week). Key H2s spot-checked on home, hub, service, destination and case-study templates — all match, hub carries 3 approved Davos Week substitutions.
CC-02 | Forbidden claims sweep | Site-wide search for international organisation wording and UN references | Zero occurrences | CLAUDE.md | C | Pass | QA-Evidence/CC-02/ | Claude Code (automated pre-audit) | 2026-08-21 | Regex sweep of raw HTML (incl. metadata + JSON-LD) on all 36 routes: 0 hits for international organisation(s), UN references (incl. standalone UN token), and all 6 named Indian states. Supplementary: 222 WEF/World Economic Forum hits — every one inside the mandated independence disclaimer (nominative trademark use per approved change log); zero outside it.
CC-03 | Consent gate works | Set consentGranted false for one state in CMS; view all pages using it | Fallback line renders; no name leaks anywhere incl. metadata | 02 s00 | C | Pass | QA-Evidence/CC-03/ | Claude Code (automated pre-audit) | 2026-08-21 | CMS toggle test deferred to E2 (Payload not embedded — environment fact). Code path verified instead: all 6 caseStudies have consentGranted:false; schema documents the gate; build-time claims gate (scripts/check-claims.mjs) run on the clone passes and enforces the named-state ban; CC-02 sweep proves zero state names in any rendered output incl. titles/meta/JSON-LD. Fallback-only rendering demonstrated.
CC-04 | Approved fallback line exact | Check hero microline, proof strip, hub, case study CS1 | Six Indian state government delegations, four WEF years, one Swiss partner | SoW 6.1 | M | Pass | QA-Evidence/CC-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Amended line 'Six Indian state government delegations. Four consecutive Davos Weeks. One Swiss partner.' renders byte-identically on all 8 pages carrying the fallback proof element (6 service proof blocks, hub proof rail, About) — zero drift. Home hero microline/proof strip and CS1 use their own spec'd wordings with approved WEF->Davos Week substitution; numeric facts (6/4 consecutive/2023-2026/one partner) consistent site-wide; no old WEF phrasing anywhere.
CC-05 | No long dashes site-wide | Crawl all rendered text; scan for em and en dashes | Zero | CLAUDE.md | M | Pass | QA-Evidence/CC-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Scanned all 36 routes: visible text, titles, meta descriptions, JSON-LD, plus a raw-HTML scan. 0 occurrences of em dash, en dash, figure dash or horizontal bar.
CC-06 | British English sample | Spelling audit across 10 pages | Consistent organise, colour, programme etc. | 02 s00 | Mn | Pass | QA-Evidence/CC-06/ | Claude Code (automated pre-audit) | 2026-08-21 | Deviation: scanned all 36 pages (superset of prescribed 10). 18 American-spelling patterns probed; 0 American spellings found. Positive evidence: organis* 52x vs organiz* 0x; programme 138x vs program 0x. Consistent British English.
CC-07 | Response promise consistency | Find every promise mention | 48 hours general, one business day MICE, identical wording | 02 s00 | M | Pass | QA-Evidence/CC-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Canonical promise sentence renders identically in footer on 32-33 pages; every other variant (home trust row/closing band, MICE CTA, enquiry intro, partner 5-business-day proposal promise) is verbatim doc-spec'd copy. Facts consistent everywhere: 48h general, one business day MICE. One cosmetic unspec'd variant: the 2 insight articles join the two sentences with ', and' — facts identical.
CC-08 | Footer treatment | Check footer on 5 templates | Descriptor, quiet group line, contact block per SoW 4.2 | SoW 4.2 | Mn | Pass | QA-Evidence/CC-08/ | Claude Code (automated pre-audit) | 2026-08-21 | Footers on 5 templates (home, service, destination-full, case-study, article) + hub: descriptor line, quiet 'A SKAAH Group company' line, contact block and independence disclaimer all present and byte-identical across templates; hub additionally carries an on-page disclaimer instance. Disclaimer wording and contact details carry [TO CONFIRM] markers by design on staging (client text/details pending — environment fact).
CC-09 | Alt text audit | Export media alts; sample 30 | Present, literal, no keyword stuffing | 02 s00 | M | Pass | QA-Evidence/CC-09/ | Claude Code (automated pre-audit) | 2026-08-21 | Photography is placeholders by design, so audited the placeholder figures' aria-labels (carrying MediaBrief alt verbatim): 30 sampled rendered names + all 64 content-layer MediaBrief alts — all present, literal scene descriptions, none empty/overlong, 0 keyword-stuffing flags. Logo imgs use empty alt inside links with aria-label='Home' (correct decorative pattern). Final <img alt> re-audit belongs to the post-shoot media pass.
CC-10 | Metadata lengths and pattern | Crawl titles and descriptions | Within 60 and 155; patterns per docs/06 s2 | 06 s2 | Mn | Pass | QA-Evidence/CC-10/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: 15 over-length metas trimmed (5 titles, 10 descriptions). Full re-crawl of all 36 routes with HTML entities decoded: zero violations (Home title exempt as written per docs/06 s2). Round 1 rendered-length figures overcounted & entities on 8 titles; corrected methodology filed.
CC-11 | MICE budget bands render | Open MICE page | Bands with footnote; editable in CMS | 02.02 C | Mn | Pass | QA-Evidence/CC-11/ | Claude Code (automated pre-audit) | 2026-08-21 | /en/services/mice-events renders 'Indicative budget bands' as a real <table> (3 formats x guests x per-person band) with the spec'd footnote 'Bands are indicative... costed line by line.' CHF values render as [TO CONFIRM] amber markers — expected at this stage. CMS editability deferred (no CMS yet — E2).
CC-12 | Legal pages final | Compare privacy, imprint, cookies to counsel-approved text | Final text, register numbers present | 02.07 B | M | Fail | QA-Evidence/CC-12/ | Claude Code (automated pre-audit) | 2026-08-21 | Judged honestly per workbook: all three pages are well-formed skeletons matching docs/02.07 B structure (controller/purposes/FADP+GDPR bases/CH-EU storage/retention/processors/rights; imprint company block; cookies category table + consent controls), BUT counsel-final text is absent: register no., VAT, address, directors, retention months and privacy mailbox render as [TO CONFIRM] markers (privacy 9, imprint 12, cookies 5). Fail pending counsel input; production marker gate would block these. Content dependency, not a template defect.
CC-13 | Davos hub complete | Check hub sections 1-8, timeline, FAQs, proof rail | All present and populated | 02.03 | M | Pass | QA-Evidence/CC-13/ | Claude Code (automated pre-audit) | 2026-08-21 | All 8 spec'd body H2 sections present and populated (3 with approved Davos Week substitutions); sticky 'On this page' nav (class verified); countdown timeline with all 6 milestones 180d->Week 0; FAQs rendered + FAQPage JSON-LD (4 Questions); proof rail with approved fallback line, stat cards (values [TO CONFIRM] by design) and links to 2 case studies; 6-frame archive-briefed gallery (placeholders pending Davos archive). Screenshots filed.
CC-14 | Hero standard read test | Functional reviewers read Home hero | Reads as capability evidenced by India, per standard | SoW 3.2 | M | Blocked | QA-Evidence/CC-14/ | Claude Code (automated pre-audit) | 2026-08-21 | Blocked: prescribed human functional review panel unavailable in this environment. Auditor observation filed with screenshot: reading order is eyebrow -> H1 'Switzerland, handled.' -> nationality-neutral capability subline -> India evidence only at step 4 in a visually subordinated 'Proven at Davos Week...' microline; in my reading it MEETS 'capability first, evidence second'. Caveats: hero film is a placeholder (brief text renders in its slot), and a spec-aware auditor cannot simulate a naive 5-second read.

## 3-Functional-Enquiry
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
FE-01 | Delegation happy path | Complete wizard with realistic TEST- data incl. one attachment | Confirm screen with SKH ref; ack mail; mailbox mail; DB row; sheet row | 02.07 | C | Pass | QA-Evidence/FE-01/ | Claude Code (automated pre-audit) | 2026-08-21 | curl multipart, XFF 10.3.1.1. 200 => SKH-20260821-0001, ownerTeam 'The delegations team', promise '48 hours'. Row persisted in data/enquiries/, PDF in data/uploads/SKH-20260821-0001/ sha256-identical to source. Untestable legs recorded honestly: segment-mailbox mail, acknowledgement mail and sheet webhook are unconfigured (no SMTP/SHEET_WEBHOOK_URL, no Hostpoint) - code path verified in lib/enquiry/deliver.ts (SMTP-unset guard logs and skips; failures queue). Delivery legs Blocked pending Hostpoint; every testable leg passed. UI journey (Playwright): full wizard incl. attachment passed, see FE-01 evidence screenshots. Playwright/Chromium UI journey (XFF 10.4.1.1): segment picker > Government delegation > steps The visit / What you need / Documents (sample.pdf via se
FE-02 | MICE RFP happy path | Complete MICE flow | Same fan-out; one business day promise shown | 02.07 | C | Pass | QA-Evidence/FE-02/ | Claude Code (automated pre-audit) | 2026-08-21 | MICE RFP, XFF 10.3.02.1. 200 => SKH-20260821-0002, response carries promise 'one business day' and ownerTeam 'The events team'; JSON persisted with segment mice.
FE-03 | Stay happy path | Complete stay flow | Full fan-out correct | 02.07 | M | Pass | QA-Evidence/FE-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Stay, XFF 10.3.03.1. 200 => SKH-20260821-0003, segment stay, ownerTeam 'The stays team' in persisted JSON.
FE-04 | Catering happy path | Complete catering flow with cuisine checkboxes | Full fan-out correct | 02.07 | M | Pass | QA-Evidence/FE-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Catering, XFF 10.3.04.1. 200 => SKH-20260821-0004, ownerTeam 'The catering team'; cuisines array persisted intact: [regional-indian, jain, vegetarian, swiss-international].
FE-05 | Agency happy path | Complete agency flow | Full fan-out correct | 02.07 | M | Pass | QA-Evidence/FE-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Agency, XFF 10.3.05.1. 200 => SKH-20260821-0005, segment agency, ownerTeam 'The partnerships team' persisted.
FE-06 | General happy path | Complete general flow | Full fan-out correct | 02.07 | M | Pass | QA-Evidence/FE-06/ | Claude Code (automated pre-audit) | 2026-08-21 | General, XFF 10.3.06.1. 200 => SKH-20260821-0006, segment general, ownerTeam 'The SKAAH team' persisted.
FE-07 | Validation and error accessibility | Submit empty and invalid fields | Inline errors, focus management, described to SR | 04 s5 | M | Pass | QA-Evidence/FE-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Empty required submit on delegation step 1: 2 inline errors, each role=alert, linked from field/fieldset via aria-describedby=<id>-error (IDs resolve). Contact step: name/organisation/email get aria-required=true, aria-invalid=true, aria-describedby -> role=alert error. Bad email format yields 'Please enter a valid e-mail address.' with same semantics. Wizard focuses step heading (tabindex=-1) on each phase change for SR orientation. DOM extracts + screenshots filed. Screen-reader output not testable (no NVDA/VoiceOver in env); judged on ARIA semantics.
FE-08 | Back lossless and draft restore | Fill 2 steps, go back, hard refresh | All data retained | 02.07 | M | Pass | QA-Evidence/FE-08/ | Claude Code (automated pre-audit) | 2026-08-21 | Filled delegation steps 1-2, Back to step 1: all values intact (radio, checkbox, number); forward again: step 2 intact. localStorage key skaah-enquiry-draft-v1 holds full values JSON. Page reload: 'We restored your draft from this device.' notice shown and all step-1 values restored. Files are excluded from drafts by design (cannot persist File objects).
FE-09 | 100 MB upload on 4G | Upload a 95-100 MB file throttled | Succeeds with per-file progress; in payload | SoW 8.1 | C | Pass | QA-Evidence/FE-09/ | Claude Code (automated pre-audit) | 2026-08-21 | 95 MB file (99,614,729 bytes, %PDF-1.4 header + urandom) to delegation (cap 100 MB), XFF 10.3.9.1. 200 => SKH-20260821-0007; persisted file sha256-identical; attachments block records exact byte count. Deviation: upload over loopback in 1.6 s - 4G throttling not available in this environment (curl, no browser network emulation for multipart API path).
FE-10 | Over-limit handling | Attempt 120 MB | Blocked with secure-link fallback message | 02.07 | M | Pass | QA-Evidence/FE-10/ | Claude Code (automated pre-audit) | 2026-08-21 | 120 MB file (125,829,129 bytes), XFF 10.3.10.1 => 422 {"error":"file_size","file":...}; no enquiry row or upload persisted. Client-side secure-link fallback confirmed in messages/en.json enquiry.attachmentsHint: 'Up to 100 MB in total (PDF, Word, Excel, PowerPoint, JPG, PNG, MP4). Larger files: we will send a secure upload link.'
FE-11 | File-type sniffing | Rename an exe to pdf; upload | Rejected by content sniffing | 05 s6 | C | Pass | QA-Evidence/FE-11/ | Claude Code (automated pre-audit) | 2026-08-21 | Real ELF binary (copy of /bin/ls, magic 7f 45 4c 46) renamed TEST-fake-document.pdf, XFF 10.3.11.1 => 422 {"error":"file_type"}; nothing persisted. Magic-byte sniffing in lib/enquiry/sniff.ts rejects despite valid extension and application/pdf content-type.
FE-12 | Honeypot and time-trap | Fill hidden field; instant submit | Silently dropped; no mail, no row | 05 s6 | M | Pass | QA-Evidence/FE-12/ | Claude Code (automated pre-audit) | 2026-08-21 | Honeypot (website filled, XFF 10.3.12.1) and time-trap (elapsedMs 100, XFF 10.3.12.2): both returned success-shaped 200 with real references (0011, 0012); both rows landed in data/spam/ only, absent from data/enquiries/; no queue/ dir created and route.ts skips deliverEnquiry() for spam, so nothing delivered.
FE-13 | Rate limiting | Ten rapid submissions | Throttled with 429 after threshold | 05 s6 | M | Pass | QA-Evidence/FE-13/ | Claude Code (automated pre-audit) | 2026-08-21 | 7 rapid submissions, all from fixed XFF 10.3.99.99: submissions 1-5 => 200 (refs 0013-0017), submissions 6-7 => 429 {"error":"rate_limited"}. Matches 5-per-10-min-per-IP spec (docs/05 s6).
FE-14 | verifiedDomain flag | Submit from a gov-style test domain address | Flag true in payload and sheet | SoW 8.1 | M | Pass | QA-Evidence/FE-14/ | Claude Code (automated pre-audit) | 2026-08-21 | Submission from desk@invest.gov.in (XFF 10.3.14.1) => SKH-20260821-0018; persisted flags.verifiedDomain=true (gov.in pattern), manualCheck=false.
FE-15 | manualCheck heuristic | Free mail plus 61+ size plus no organisation | Flag true | 02.07 | Mn | Pass | QA-Evidence/FE-15/ | Claude Code (automated pre-audit) | 2026-08-21 | gmail.com sender + delegation sizeBand 61-plus + empty organisation (XFF 10.3.15.1) => SKH-20260821-0019; persisted flags.manualCheck=true, verifiedDomain=false. Matches heuristic in lib/enquiry/flags.ts.
FE-16 | Reference format | Three submissions | SKH-YYYYMMDD-#### unique and sequential | 02.07 | Mn | Pass | QA-Evidence/FE-16/ | Claude Code (automated pre-audit) | 2026-08-21 | Three submissions => SKH-20260821-0020/-0021/-0022: format SKH-YYYYMMDD-#### with today's UTC date, unique, strictly sequential. Observation (informational): nextReference() runs before attachment validation, so rejected uploads (FE-10/11) consume sequence numbers - gaps 0008/0009 in enquiries/; uniqueness and ordering unaffected, no spec clause forbids gaps.
FE-17 | Ack mail content per segment | Review all six acknowledgement mails | Correct promise, reference, contact block | 02.07 | M | Pass | QA-Evidence/FE-17/ | Claude Code (automated pre-audit) | 2026-08-21 | Template audit of deliver.ts (live mail Blocked - SMTP unset, no Hostpoint; sendMail guard logs and skips). Template contains: reference (subject + body), per-segment promise via spec.promise ('The events team replies within one business day' for mice, '48 hours' others), and a signature/contact block ('SKAAH Hospitality GmbH / Opfikon (Zurich Airport), Switzerland'). Caveat: contact block has no phone/e-mail line - phone/WhatsApp numbers are [TO CONFIRM] and unconfigured pre-staging.
FE-18 | Mailbox routing | One submission per segment | Arrives at its nominated Hostpoint mailbox | 08 s4 | C | Blocked | QA-Evidence/FE-18/ | Claude Code (automated pre-audit) | 2026-08-21 | Live mailbox routing untestable: no Hostpoint mailboxes/SMTP exist yet. Programmatic pre-check filed and PASSED: .env.example SEGMENT_MAILBOXES maps all six segments (delegations@/mice@/stays@/catering@/partners@/enquiry@skaahhospitality.com, addresses [TO CONFIRM]); deliver.ts segmentMailbox() resolves per payload.segment and mails payloadSummary with subject 'New <segment> enquiry <ref>', queueing on failure.
FE-19 | Payload schema complete | Inspect stored JSON | All fields per docs/05 s7 incl. flags, consent, utm | 05 s7 | M | Pass | QA-Evidence/FE-19/ | Claude Code (automated pre-audit) | 2026-08-21 | Field-by-field diff of persisted SKH-20260821-0001.json vs docs/05 s7: 22/22 checks OK - reference format, segment enum, ISO submittedAt, all 6 contact fields, segment details, attachments[{file,bytes,url}], flags{verifiedDomain,manualCheck,utm}, consent{privacyVersion,acceptedAt}, locale; no undocumented top-level fields. Deviation noted: attachments[].url is data://uploads/... not a signed bucket URL - documented interim DECISION in lib/enquiry/store.ts (local Swiss NVMe until bucket exists, signed URLs in task T4.3).
FE-20 | Tracking sheet integrity | Compare appended row to payload | Fields align; status and owner columns present | SoW 8.1 | M | Blocked | QA-Evidence/FE-20/ | Claude Code (automated pre-audit) | 2026-08-21 | Live tracking sheet untestable: SHEET_WEBHOOK_URL unset, no Google Sheet exists. Pre-check filed and PASSED: deliver.ts webhook body carries all SoW fields - reference, segment, date (submittedAt), status ('new'), owner (empty for ops assignment), estimatedValue, plus verifiedDomain/manualCheck; non-OK response throws and queues (failure path proven live in FE-21).
FE-21 | Failure fallback | Break mail creds on staging; submit | User sees fallback keeping data, offering WhatsApp and mail; retry queue logs and alerts | 07 T4.6 | M | Pass | QA-Evidence/FE-21/ | Claude Code (automated pre-audit) | 2026-08-21 | Second instance started on :3223 with SHEET_WEBHOOK_URL=http://127.0.0.1:9/dead and DATA_DIR=data-fe21. Submission (XFF 10.3.21.1) => visitor got 200 + SKH-20260821-0001 in 22 ms despite dead webhook; row persisted; failed job queued at data-fe21/queue/sheet-*.json {kind:'sheet', error:'TypeError: fetch failed'}. Server killed after (incl. orphaned next-server child; port 3223 verified refused; main :3222 unaffected). Splits: UI fallback screen is agent 4's; retry worker + alert-on-final-failure not yet implemented (task T4.6 per store.ts) - alerting Blocked as workbook anticipates. UI fallback screen (Playwright): error panel with retry, WhatsApp and mail links, data retained. page.route aborted /api/enquiry (XFF 10.4.21.1); submit => 'Something went wrong.' screen with Try again button, WhatsAp
FE-22 | WhatsApp FAB and phone links | Check 3 templates and /enquiry | Correct deep links, events fire, FAB hidden on enquiry | 04 C18 | Mn | Pass | QA-Evidence/FE-22/ | Claude Code (automated pre-audit) | 2026-08-21 | On /en, /en/services/government-delegations, /en/davos-week: FAB (a.fixed, aria-label 'Chat on WhatsApp') has opacity 0 + pointer-events none at scrollY 0 and 300, opacity 1 + clickable at 900 (threshold is scrollY>600 per WhatsAppFab.tsx). On /en/enquiry the FAB is not rendered at all even at 1200px scroll. All WhatsApp links point at https://wa.me/... As stated in env facts, the number is the placeholder '0' (NEXT_PUBLIC_WHATSAPP_NUMBER unset, [TO CONFIRM]); no tel: links rendered (phone also unconfirmed).

## 4-SEO-Schema
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
SS-01 | Full crawl metas | Screaming Frog crawl | No missing or duplicate titles and descriptions | 06 s2 | M | Pass | QA-Evidence/SS-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Deviation: custom Node crawler (script filed) instead of Screaming Frog. All 36 sitemap routes HTTP 200; titles 36/36 present 0 dupes; meta descriptions 36/36 present 0 dupes. Side observation (not this test's criteria): ~12 titles exceed the docs/06 s2 60-char guidance (home ~72 decoded) and 10 descriptions exceed 155 (max 219).
SS-02 | Canonicals consistent | Crawl canonicals and slash policy | Self-canonical everywhere, one policy | 06 s4 | M | Pass | QA-Evidence/SS-02/ | Claude Code (automated pre-audit) | 2026-08-21 | rel=canonical extracted on all 36 routes: every one an absolute https://skaahhospitality.com/en... URL, exactly self-referencing, zero trailing slashes = single consistent no-trailing-slash policy.
SS-03 | Sitemap valid and complete | Validate; count against inventory | All 27 plus legal, no staging URLs | 06 s4 | M | Pass | QA-Evidence/SS-03/ | Claude Code (automated pre-audit) | 2026-08-21 | xmllint: well-formed. 36 URLs = 25 concrete inventory routes + 6 case studies + 2 articles + 3 legal, exact match to docs/01 s3; hub at /davos-week per approved change log; no strays, no missing. Deviation: sitemaps.org XSD validation impossible (external fetch blocked).
SS-04 | Robots split | Check staging and production robots | Staging disallow with auth; production open | 06 s4 | C | Pass | QA-Evidence/SS-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Live staging /robots.txt = 200 'User-Agent: *, Disallow: /' (full disallow proven). Production branch proven by source: app/robots.ts returns allow / + disallow /api/ + sitemap URL when NEXT_PUBLIC_ENV=production (lib/site.ts isProductionEnv). Only staging is live here; docs/06 staging basic-auth is host-level, untestable pre-staging.
SS-05 | JSON-LD zero errors | Rich Results test on each template type | Organization, LocalBusiness, Service, FAQ, Article, Breadcrumb all validate | 06 s3 | M | Pass | QA-Evidence/SS-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Deviation: Google Rich Results unavailable; local validator parsed all 137 ld+json blocks across 36 routes and checked required props per type: 0 parse errors, 0 missing props. Coverage matches docs/06 s3 (Org+WebSite sitewide, TravelAgency on About, Service+FAQPage on 7 services, Article on 6+2, BreadcrumbList everywhere except Home). FAQ questions spot-checked visible on page. sameAs/telephone/geo omissions are [TO CONFIRM] truth-discipline, not errors.
SS-06 | NAP alignment | Compare footer, About, GBP | Identical name, address, phone | 06 s6 | Mn | Pass | QA-Evidence/SS-06/ | Claude Code (automated pre-audit) | 2026-08-21 | Footer, About and TravelAgency JSON-LD identical at the level of confirmed facts: SKAAH Hospitality GmbH, Opfikon (Zurich Airport), Switzerland / Opfikon-Zurich-CH PostalAddress, enquiry@skaahhospitality.com. Phone is [TO CONFIRM] consistently everywhere (no tel: link, no schema telephone). GBP does not exist yet (docs/06 s6 launch task) so no GBP comparison possible.
SS-07 | Redirect map live | Test skaah.com/hospitality, 5 legacy URLs, www and http, .ch if live | All 301 to correct targets | 06 s5 | M | Pass | QA-Evidence/SS-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Split result as instructed. App half Pass: all four renamed paths (/davos-wef, /en/davos-wef, /en/insights/wef-delegation-countdown, /en/work/first-time-state-delegation-wef) return 308 to the correct /en/davos-week / davos-delegation-countdown / first-time-state-delegation-davos targets, final 200 (next.config.ts permanent:true; Next emits 308 for permanent). Host half Blocked: skaah.com/hospitality legacy 301s are host-level on the group domain, no Hostpoint/DNS exists pre-staging; legacy URL list itself still [TO CONFIRM] in docs/06 s5.
SS-08 | Social cards | Preview 5 pages in WhatsApp and LinkedIn | Branded 1200 by 630 frames render | 06 s4 | Mn | Pass | QA-Evidence/SS-08/ | Claude Code (automated pre-audit) | 2026-08-21 | All 5 sampled pages (home, hub, flagship service, case study, article) carry full og:title/description/image/url/type + twitter summary_large_image set. og:image everywhere is the square group logo (resolves 200); the branded 1200x630 OG frame template (docs/06 s4 E1 task) is not yet designed, as the workbook anticipates. External card debuggers unavailable; tag inspection only.
SS-09 | Error status codes | curl an unknown URL and force a 500 | Real 404 and 500 statuses with designed pages | 04 s6 | M | Pass | QA-Evidence/SS-09/ | Claude Code (automated pre-audit) | 2026-08-21 | 404 half judged per workbook: unknown /en/* URL returns real HTTP 404 with the designed page (h1 'This page has moved on.', recovery links); non-prefixed unknown URL 307s to /en then 404s. Minor finding: the 404 response has NO <title> tag. 500 half not exercised (would require breaking the clone); app/[locale]/error.tsx client boundary exists and is filed. Round 2: root layout fallback metadata added; the 404 response now carries a title (verified live), status still a real 404.
SS-10 | RSS valid | Run feed validator | Passes | 06 s4 | Mn | Pass | QA-Evidence/SS-10/ | Claude Code (automated pre-audit) | 2026-08-21 | /rss.xml 200, well-formed per xmllint, rss version 2.0 with required channel title/link/description plus language, lastBuildDate, atom:link self; 2 items (= 2 seeded articles) each with title/link/guid/pubDate/description. Deviation: W3C feed validator unavailable, local parse + checklist.
SS-11 | Internal linking rules | Sample all 7 service pages | Hub, destination, case study and article links present | 06 s2 | Mn | Pass | QA-Evidence/SS-11/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: Plan deeper cross-links block added to the service template with a per-service map. Re-crawl: all 7 service pages now link the hub, one destination guide, one case study and one article in editorial main content. 0 of 7 became 7 of 7.
SS-12 | hreflang readiness | Inspect locale config and generator test | Single locale clean; matrix logic unit-tested | SoW 5.2 | Mn | Pass | QA-Evidence/SS-12/ | Claude Code (automated pre-audit) | 2026-08-21 | i18n/routing.ts: single locale ['en'], localePrefix 'always' so extra locales attach without URL changes; next-intl middleware ready for negotiation. Live crawl: 0 hreflang links emitted across all 36 routes — correct at single locale per docs/06 s4 (matrix auto-generates when locale >1). Sitemap per-locale-ready (/en URLs).
SS-13 | Analytics events | Trigger the 12 events from docs/06 s7 | Each visible in the analytics debugger | 06 s7 | M | Pass | QA-Evidence/SS-13/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: article_read wired via ReadTracker (75% scroll, mirrors case_study_read) on the article template; phone_click wired via PhoneLink, which renders a tel: link firing the event as soon as NEXT_PUBLIC_PHONE_NUMBER is configured (marker until then). 11 of 13 events wired; film_play/film_pause remain N.A. pending the film master (FilmBlock carries both for when it lands).
SS-14 | Consent behaviour | Reject then accept flows; inspect network | Nothing non-essential loads before consent; choices persist | 05 s8 | C | Pass | QA-Evidence/SS-14/ | Claude Code (automated pre-audit) | 2026-08-21 | Fresh context: zero third-party scripts, zero cookies (document.cookie and context cookies empty), no window.plausible before any choice; banner open. Necessary-only: still nothing after reload, banner stays closed, localStorage skaah-consent-v1 {analytics:false} persists. Allow analytics: consent persists {analytics:true} across reload; plausible script still absent because NEXT_PUBLIC_PLAUSIBLE_DOMAIN is unset - conditional verified in DOM and in ConsentBanner.tsx:45-52 (script renders only when analyticsAllowed && domain). Zero external network requests observed across all phases. Consent stored in localStorage, not a cookie.

## 5-Performance
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
PF-01 | LCP Home | Moto-class device, 4G, film enabled; Lighthouse plus WebPageTest | Under 2.0 s; LCP element is the hero poster | 04 s6 | C | Fail | QA-Evidence/PF-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Lighthouse 12 mobile emulation, default simulated 4G (lantern), Chromium 1194 on a datacentre host (not a Moto-class device) — deviation noted. LCP = 3000 ms simulated, over the docs/04 2.0 s Lighthouse-CI-mobile budget (perf score 0.95; FCP 910 ms; observed unthrottled LCP 118 ms). LCP element is NOT the poster stand-in: it is the hero subline paragraph (section.relative > div.container-site > p.mt-6) because the poster is a CSS gradient pending media, so no image candidate exists. The 3.0 s is driven by the render-blocking CSS + five preloaded self-hosted WOFF2 fonts chain under simulated 4G.
PF-02 | LCP Government Delegations | Same method | Under 2.0 s | 04 s6 | M | Fail | QA-Evidence/PF-02/ | Claude Code (automated pre-audit) | 2026-08-21 | Same lab config/deviation as PF-01. LCP = 3022 ms simulated (> 2.0 s budget); FCP 914 ms, TBT 86 ms, perf 0.94. LCP element = hero subline text (p.mt-5); same font/CSS chain cause.
PF-03 | LCP MICE | Same method | Under 2.0 s | 04 s6 | M | Fail | QA-Evidence/PF-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Same lab config/deviation as PF-01. LCP = 3013 ms simulated (> 2.0 s budget); FCP 913 ms, TBT 83 ms, perf 0.94. LCP element = hero subline text.
PF-04 | LCP Davos hub | Same method | Under 2.0 s | 04 s6 | M | Fail | QA-Evidence/PF-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Same lab config/deviation as PF-01. LCP = 3004 ms simulated (> 2.0 s budget); FCP 912 ms, TBT 78 ms, perf 0.94. LCP element = hero subline text on /en/davos-week (approved Davos Week hub route).
PF-05 | CLS key templates | Lab plus field-style runs | Under 0.1 everywhere | 04 s6 | M | Pass | QA-Evidence/PF-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: the enquiry wizard column and its Suspense fallback reserve min-h-34rem so hydration cannot push the side rail. Lighthouse mobile: /en/enquiry CLS now 0 (was 0.3057), LCP 1.7 s; the other four templates unchanged at CLS 0.
PF-06 | INP | Interaction tests on wizard and menus | Under 200 ms | 04 s6 | M | Pass | QA-Evidence/PF-06/ | Claude Code (automated pre-audit) | 2026-08-21 | Deviation: real INP is a field interaction metric a lab navigation run cannot measure; TBT used as the lab proxy as the workbook prescribes. TBT 42.5/86/83/78/89 ms across the five routes — all far under the ~200 ms proxy threshold, with wide margin, so judged Pass on the proxy; no actual interactions were exercised.
PF-07 | JS budgets | Bundle analysis | At most 170 KB gz content routes; 240 KB enquiry | 04 s6 | Mn | Pass | QA-Evidence/PF-07/ | Claude Code (automated pre-audit) | 2026-08-21 | pnpm build rerun on commit 8b6e82d in an isolated hardlink copy (live staging server untouched). next build gzip First Load JS: content routes 120–125 kB (largest /[locale]/work 125 kB) vs 170 kB budget; /enquiry 130 kB vs 240 kB budget; shared baseline 102 kB, middleware 46.3 kB. Full route table filed.
PF-08 | Film loading behaviour | Network waterfall; toggle reduced motion and Save-Data | Video only after LCP; poster-only under both toggles | 04 C03 | M | N.A. | QA-Evidence/PF-08/ | Claude Code (automated pre-audit) | 2026-08-21 | Hero film does not exist by design (poster-first gradient stand-in; DECISION note in HeroFilm.tsx pending docs/02 media plan). No <video> element exists in the tree, so there is no loading behaviour to test. Gating design verified in code/docs: HeroFilm comment specifies idle-injected video gated on Save-Data and prefers-reduced-motion per docs/04 §6/§73; global prefers-reduced-motion CSS blocks exist (globals.css:62,185); the video-swap client component itself is not yet implemented. Staging-only film-brief note is gated off production (NEXT_PUBLIC_ENV check).
PF-09 | Image pipeline | Audit 10 images | AVIF or WebP with responsive srcset and sizes | 04 s6 | Mn | Pass | QA-Evidence/PF-09/ | Claude Code (automated pre-audit) | 2026-08-21 | Photography pending — the only raster content image is the Group logo emblem. It uses next/image (SiteLogo.tsx), width/height declared, priority; live check shows a single /_next/image request served as image/webp 4.2 kB (optimizer active; curl probe confirms webp re-encode of the PNG source). No raw <img> anywhere; other assets are SVG. Judged Pass for what exists; note next.config has no images{} block so AVIF is not enabled — revisit when the Davos archive / Phase 1 shoot media lands.
PF-10 | Geo probes | WebPageTest Zurich and Mumbai | TTFB documented; CH under 0.8 s, IN under 1.6 s | 05 s5 | Mn | Blocked | QA-Evidence/PF-10/ | Claude Code (automated pre-audit) | 2026-08-21 | WebPageTest Zurich/Mumbai probes unavailable (no external SaaS, and no Hostpoint server/DNS exists yet — pre-staging). Programmatic pre-check filed: local TTFB on the staging build 3.7–4.8 ms across /en, /en/davos-week, /en/services/government-delegations, /en/enquiry (12 runs), i.e. server render cost is negligible; geo latency will dominate and must be measured post-deployment.

## 6-Accessibility
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
AC-01 | axe scan per template | Run axe on all 15 templates | Zero critical issues | 04 s5 | C | Pass | QA-Evidence/AC-01/ | Claude Code (automated pre-audit) | 2026-08-21 | AxeBuilder (@axe-core/playwright, Chromium 1194) on all 15 workbook templates + /en/privacy: ZERO critical violations on every page. Reported non-critical totals: serious color-contrast 247 nodes (detailed under AC-05), serious scrollable-region-focusable 2, moderate region 15, moderate heading-order 3, minor aria-allowed-role 25. Full JSON filed (node html trimmed to fit size cap).
AC-02 | Keyboard-only full journey | Home to service to hub to full enquiry incl. upload, keyboard only | Complete without traps | 04 s5 | C | Pass | QA-Evidence/AC-02/ | Claude Code (automated pre-audit) | 2026-08-21 | Keyboard-only journey (full Tab path logged): consent dismissed via Tab+Enter; Services dropdown opened with Enter, Tab into it, Enter navigates; header Davos Week and Start an enquiry reached by Tab+Enter; segment picked with Enter; wizard step completed typing-only; focus moves to step heading on each phase change; 60-Tab trap sweep on contact step found no trap. Supplementary radio-arrow-key-check.txt: radio chip groups respond to ArrowDown/ArrowUp/Space (delegation purpose group).
AC-03 | Focus visibility | Tab across navy and light sections | 2 px visible ring everywhere | 04 s5 | M | Pass | QA-Evidence/AC-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Computed :focus-visible outlines sampled across 3 templates after keyboard focus: dark surfaces (header, hero CTAs, dark sections) = 2px solid rgb(191,160,90) gold-500; light surfaces = 2px solid rgb(22,64,105) navy-900; offset 2px everywhere. Minor observation (not a failure): Tailwind transition-colors also transitions outline-color, so on those elements the ring colour fades in from currentColor over 200ms (ring itself present from first frame; disabled under prefers-reduced-motion). Initial instant-sample readings in the log's first pass reflect that transition, corrected log filed.
AC-04 | Skip link | First tab on each template | Skip to content works | 04 s5 | Mn | Pass | QA-Evidence/AC-04/ | Claude Code (automated pre-audit) | 2026-08-21 | On /en, /en/davos-week, /en/work: first Tab focuses visible 'Skip to content' (href=#main, 146x42px at 16,16). Enter sets #main as fragment target and the next Tab lands inside #main (hero CTA / breadcrumb), header bypassed - functional check filed. Note: #main has no tabindex=-1, so activeElement stays body after activation and skipping relies on browser sequential-focus-from-fragment behaviour (works in Chromium; only browser available).
AC-05 | Contrast checks | Verify body, eyebrows, gold usage against tokens | AA met; gold only in permitted roles | 04 s1 | M | Pass | QA-Evidence/AC-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: AA-compliant small-gold tokens added (gold-700 #866B26 for light surfaces, gold-400 #D2B878 for navy, DECISION documented in globals.css); footer copy moved to ice tokens; small stone-400 text raised to stone-500; gold buttons and outline links moved to gold-400 fills; header idle state raised to navy-950/90 so it never sits translucent over light content; placeholder scrim strengthened. axe color-contrast: 0 nodes across 10 templates (was 247), 0 critical violations.
AC-06 | Forms announced | NVDA and VoiceOver on wizard errors | Labels and errors announced via describedby | 04 s5 | M | Blocked | QA-Evidence/AC-06/ | Claude Code (automated pre-audit) | 2026-08-21 | NVDA/VoiceOver unavailable (Linux container). Programmatic pre-check POSITIVE: errors render as p[role=alert][id=<field>-error]; errored fieldsets carry legend + aria-describedby resolving to the alert; text fields have label[for], aria-required/invalid/describedby; radios/checkboxes implicitly labelled; honeypot aria-hidden. Residual for the human SR pass: no focus move to first error and no aria-live summary after failed validation.
AC-07 | Accordion and menu ARIA | Inspect patterns and SR behaviour | APG-conformant states | 04 s5 | M | Pass | QA-Evidence/AC-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: Services and Destinations disclosure buttons and the mobile burger now carry aria-controls (resolvable panel ids) and aria-haspopup alongside aria-expanded; FAQ accordion was already APG-conformant. Verified in rendered DOM.
AC-08 | Film pause control | Locate and operate | Present, keyboard reachable | 04 s5 | M | N.A. | QA-Evidence/AC-08/ | Claude Code (automated pre-audit) | 2026-08-21 | No hero film exists yet by design: zero <video>/autoplay in codebase or rendered /en (placeholder pending Davos archive / Phase 1 shoot). Spec requirement stands for the film build: docs/04 C03 pause/play control bottom-right, film never conveys sole meaning.
AC-09 | Landmarks and headings | Audit structure | One h1, logical order, landmarks present | 04 s5 | Mn | Pass | QA-Evidence/AC-09/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 retest: sr-only h2 headings added above the card grids on /en/services, /en/destinations and /en/work; h1-h2-h3 order verified in rendered HTML. All 36 routes clean.
AC-10 | 200 percent zoom | Zoom key templates | No loss of content or function | 04 s5 | M | Pass | QA-Evidence/AC-10/ | Claude Code (automated pre-audit) | 2026-08-21 | Emulation method: 640px viewport at desktop Chromium UA (equivalent of 200% on 1280; native browser-zoom unavailable headless). /en, /en/davos-week, /en/enquiry: scrollWidth==clientWidth (no horizontal scroll), h1/nav/enquiry CTA present and visible, wizard advances to step 1 and renders fieldsets at this width. Screenshots filed.
AC-11 | Screen reader task pass | NVDA and VoiceOver: find a service and submit a test enquiry | Both complete | 04 s5 | M | Blocked | QA-Evidence/AC-11/ | Claude Code (automated pre-audit) | 2026-08-21 | NVDA and VoiceOver do not exist in this Linux/Chromium-only environment; a real screen-reader task pass is impossible. Programmatic proxies filed under AC-06/AC-07/AC-09. Must be run by a human before launch.
AC-12 | Target sizes | Sample touch targets | At least 24 px | 04 s5 | Mn | Pass | QA-Evidence/AC-12/ | Claude Code (automated pre-audit) | 2026-08-21 | 24 elements sampled across /en, /en/davos-week, /en/enquiry incl. per-page smallest. All buttons, CTAs, form controls, segment cards, header items, FAB >= 24x24 (33-420px). Below-24 cases all fall under WCAG 2.5.8 exceptions, measured: stacked footer text links h=17px but 36-37px centre spacing (spacing exception); mailto link inline in text (inline exception); skip link 1x1 only while sr-only hidden (146x42 when focused, not a pointer target when hidden). Workbook's literal '>=24x24 each' is stricter than SC 2.5.8; analysis filed in evidence.

## 7-Security-Residency
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
SR-01 | Swiss server evidence | Archive Hostpoint contract page, IP geolocation, traceroute | Server confirmed in Switzerland; evidence filed | 08 s5 | C | Blocked | QA-Evidence/SR-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Pre-staging: no Hostpoint server exists to evidence Swiss residency. Design verified in docs/08 s1/s5 (Swiss data centre, all data in CH); code stores everything under DATA_DIR local disk (lib/enquiry/store.ts) which maps to Swiss NVMe on the Flex server.
SR-02 | All enquiry endpoints on the Swiss host | Inspect DNS and hosts for POST, uploads, attachment URLs | Same Hostpoint server only; no third-party storage | 08 s5 | C | Blocked | QA-Evidence/SR-02/ | Claude Code (automated pre-audit) | 2026-08-21 | Pre-staging: /api/enquiry runs only on the local QA server. Pre-check: persistence is DATA_DIR JSON on local disk; SMTP/webhook fan-out unset here and queue-on-failure by design; no third-country calls in code. Re-test on the Hostpoint host.
SR-03 | Signed URL policy | Fetch attachment link; tamper; simulate expiry | 30-day signed; unauthorised blocked | 05 s6 | M | Fail | QA-Evidence/SR-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Genuine gap vs docs/05 s6 (signed 30-day URLs for attachment access): persistAttachment() writes to local disk and returns a data:// pseudo-URL; no URL-signing code exists in the repo. A DECISION comment (store.ts lines 52-56) defers signing to task T4.3 pending the spike-S0 storage decision — documented deferral, but the control is not implemented as built.
SR-04 | Security headers grade | securityheaders.com on production | Grade A or better; CSP with nonces | 05 s6 | M | Fail | QA-Evidence/SR-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Round 2 improvement, requirement not yet literally met: Content-Security-Policy now sent (default-src self; script/connect allowances for Plausible only; frame-ancestors none; object-src none; base-uri and form-action self) with a documented DECISION: per-request nonces would force dynamic rendering and forfeit the static prerendering the CWV budgets depend on, so the nonce upgrade is scheduled at the Hostpoint Nginx layer (docs/08). docs/05 s6 asks for CSP with nonces, so the row stays Fail until that lands; header grade materially improved from round 1.
SR-05 | TLS grade | SSL Labs | Grade A; modern protocols only | 08 s3 | M | Blocked | QA-Evidence/SR-05/ | Claude Code (automated pre-audit) | 2026-08-21 | No TLS endpoint exists: QA build is plain HTTP on 127.0.0.1:3222; TLS terminates at the future Hostpoint Nginx proxy (Let's Encrypt, docs/08). SSL Labs also unreachable. No pre-check possible without a TLS listener.
SR-06 | Admin authentication | Attempt weak login; session rules; staging basic auth | Strong auth enforced; staging protected | 05 s6 | C | Blocked | QA-Evidence/SR-06/ | Claude Code (automated pre-audit) | 2026-08-21 | No admin surface exists: Payload CMS is epic E2, not embedded (no payload dependency; GET /admin => 404, so nothing unauthenticated is exposed). Staging basic auth is Hostpoint Control-Panel-level and no server exists. Critical launch gate — re-test with E2 + server.
SR-07 | No secrets in client | Grep built JS for keys and tokens | None | 05 s6 | C | Pass | QA-Evidence/SR-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Grepped .next/static (client-delivered) and .next/standalone for env var names, key/token/secret/password patterns and every non-empty .env.example value. Client bundles: zero env names, zero mailbox/from-address values (only the public enquiry@ contact address that page content displays by design); all 32 'password' hits are React input-type handling and URL-polyfill internals (contexts archived). Standalone server bundle: no hardcoded secret literals, no .env files. Note: no real secrets exist in this pre-staging environment; scan proves the build pipeline embeds none of the placeholder values.
SR-08 | Runtime env protection | Check shared/.env permissions and location | chmod 600, outside web root | 08 s6 | M | Blocked | QA-Evidence/SR-08/ | Claude Code (automated pre-audit) | 2026-08-21 | Server-side control (.env chmod 600 on Flex server, docs/08 s5/s6). Local pre-checks run and clean: gitleaks 8.24.3 full-history scan (7 commits) — no leaks; .gitignore covers .env variants (verified with git check-ignore); only .env.example committed.
SR-09 | Restore drill | Restore yesterday's backup to scratch and boot | Documented successful drill | 08 s4 | C | Blocked | QA-Evidence/SR-09/ | Claude Code (automated pre-audit) | 2026-08-21 | Pre-staging: Hostpoint snapshots/backups and the nightly export archive do not exist; nothing to restore from. No meaningful local equivalent for a provider-backup restore drill.
SR-10 | Nightly export archive | Inspect backups folder | Present, rotating 30 days | 08 s4 | Mn | Blocked | QA-Evidence/SR-10/ | Claude Code (automated pre-audit) | 2026-08-21 | Nightly cron is server-side (docs/08 s3). Pre-check: export script exists and is wired — package.json export:content -> scripts/export-content.ts dumping the typed content layer to exports/<date>/ JSON + media manifest. Cron registration and tar.gz rotation are server-side by design.
SR-11 | Retention purge job | Inspect job; dry run | Configured per privacy policy | 05 s6 | M | Blocked | QA-Evidence/SR-11/ | Claude Code (automated pre-audit) | 2026-08-21 | Server-side scheduling unavailable pre-staging, BUT genuine open item recorded: grep over lib/app/scripts finds NO purge job code at all, and the retention period is still [TO CONFIRM: months] in docs/05 s6 and docs/08 s5. The job must be built and the months confirmed before launch — nothing exists to schedule even once the server does.
SR-12 | Admin audit log | Perform an edit; view log | User, action, time recorded | 05 s6 | Mn | Blocked | QA-Evidence/SR-12/ | Claude Code (automated pre-audit) | 2026-08-21 | Admin audit log attaches to the Payload admin (epic E2) which is not yet embedded; no admin actions exist to log. Pre-check: no audit-log implementation in code (expected at this phase).
SR-13 | Mail authentication | mail-tester.com on ack mail | Score at least 9; SPF, DKIM, DMARC pass | 08 s4 | M | Blocked | QA-Evidence/SR-13/ | Claude Code (automated pre-audit) | 2026-08-21 | No mailboxes, DNS zone or SMTP exist (docs/08 s5 SPF/DKIM/DMARC; spike S0 step 5 deliverability test). mail-tester unreachable and no sending domain exists. SMTP_* unset in this environment; mail fan-out queues to DATA_DIR/queue.

## 8-Compat-Matrix
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
CM-01 | Journey on Chrome, Windows | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | M | Pass | QA-Evidence/CM-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Chromium 1280x800 (XFF 10.4.2.1): Home > Services dropdown > Government & Diplomatic Delegations > header Davos Week hub > Start an enquiry > general segment submitted (HTTP 200, SKH-20260821-0024). scrollWidth==innerWidth (1280) at all 7 checkpoints, no layout breaks in screenshots. Note: desktop Chrome emulated via bundled Chromium, not branded Chrome.
CM-02 | Journey on Edge, Windows | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | Mn | Blocked | QA-Evidence/CM-02/ | Claude Code (automated pre-audit) | 2026-08-21 | Edge unavailable (Chromium only in container, no SaaS device cloud). Chromium/Blink coverage by agent 4 makes Edge risk low but unverified.
CM-03 | Journey on Firefox, Windows | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | Mn | Blocked | QA-Evidence/CM-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Firefox/Gecko unavailable; genuinely untested engine. Chromium coverage by agent 4 noted; run on real Firefox before launch.
CM-04 | Journey on Safari, macOS | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | M | Blocked | QA-Evidence/CM-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Safari macOS/WebKit unavailable; genuinely untested engine. Chromium coverage by agent 4 noted.
CM-05 | Journey on Safari, iPhone (iOS current) | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | C | Blocked | QA-Evidence/CM-05/ | Claude Code (automated pre-audit) | 2026-08-21 | iOS Safari unavailable (no devices/simulators/SaaS). Critical launch gate for the delegation audience — must run on real iPhone before launch. Chromium mobile-viewport coverage by agent 4 is not an engine substitute.
CM-06 | Journey on Chrome, mid-range Android | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | C | Pass | QA-Evidence/CM-06/ | Claude Code (automated pre-audit) | 2026-08-21 | Pixel-class emulation: 393x851, Android mobile UA, isMobile+hasTouch, DPR 2.75 (XFF 10.4.6.1). Journey completed via hamburger mobile menu (nav aria-label='Mobile') for every hop incl. 'Start an enquiry' CTA; submission SKH-20260821-0025; no horizontal overflow at any of 7 checkpoints. Deviation per env facts: Chromium device emulation, not a real Android device.
CM-07 | Journey on Safari, iPad | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | M | Blocked | QA-Evidence/CM-07/ | Claude Code (automated pre-audit) | 2026-08-21 | iPad Safari unavailable; same constraint as CM-05.
CM-08 | Journey on 360 px width | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | M | Pass | QA-Evidence/CM-08/ | Claude Code (automated pre-audit) | 2026-08-21 | 360x740 mobile emulation (XFF 10.4.8.1): full journey via mobile menu completed, submission SKH-20260821-0026. document.scrollingElement.scrollWidth == innerWidth (360) at all 7 checkpoints - no horizontal overflow; menu usable (screenshot 02-menu-open).
CM-09 | Journey on 768 px width | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | Mn | Pass | QA-Evidence/CM-09/ | Claude Code (automated pre-audit) | 2026-08-21 | 768x1024 (XFF 10.4.9.1): journey completed, submission SKH-20260821-0027; scrollWidth==768 at all 7 checkpoints. At 768px the header uses the hamburger menu (desktop nav appears at lg/1024) - menu usable.
CM-10 | Journey on 1440 px width | Browse Home, one service, the hub, then submit a TEST enquiry | No layout breaks; journey completes; film or poster correct | 04, 01 | Mn | Pass | QA-Evidence/CM-10/ | Claude Code (automated pre-audit) | 2026-08-21 | 1440x900 (XFF 10.4.10.1): journey via desktop Services dropdown completed, submission SKH-20260821-0028; scrollWidth==1440 at all 7 checkpoints; no layout breaks.

## 9-CMS-Editorial
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
CE-01 | Edit and publish hero line | Ms. Revathi, unaided, edits Home hero subline and publishes | Live within minutes, no developer help | 01 s4 | M | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/.
CE-02 | Create article from brief 3 | Build the visas article from docs/02.06 outline | Published with meta, image, alt | 01 s4 | M | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/.
CE-03 | Alt enforcement | Attempt image upload without alt | Blocked by validation | 05 s4 | M | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/. Alt-required validation is a Payload field rule (T2.1), not yet built.
CE-04 | Reorder work listing | Change case study order | Reflected on site | 01 s4 | Mn | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/.
CE-05 | Update MICE bands | Edit a band value | Table updates | 02.02 C | Mn | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/. Bands currently render from the typed content layer (CC-11 Pass).
CE-06 | Edit an FAQ | Change one hub FAQ | Page and schema update | 06 s3 | Mn | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/.
CE-07 | Change a meta title | Edit one page's metaTitle | Rendered and within limits | 06 s2 | Mn | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/.
CE-08 | Toggle notice bar | Enable C29 with a message; disable | Appears and disappears | 04 C29 | Mn | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/. C29 NoticeBar component also missing (CA-05).
CE-09 | Role boundary | Editor attempts seoDefaults global | Blocked by role | 05 s4 | M | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Payload CMS not yet embedded (epic E2 open, docs/07 T0.3/T2.x); no admin surface exists to exercise. See QA-Evidence/CE-ALL/. Editor role boundary (T2.5) not yet built.
CE-10 | Run the export | Follow the documented export procedure | Archive produced without developer help | SoW 9.2 | C | Blocked | QA-Evidence/CE-ALL/ | Claude Code (automated pre-audit) | 2026-08-21 | Blocked on the editorial-independence condition (Ms. Revathi unaided, post-training). The export procedure itself was proven under CA-12, where a completeness defect was found (stale davos-wef import). See QA-Evidence/CE-ALL/ and QA-Evidence/CA-12/.

## 10-Deploy-Ops
ID | Test case | Steps / method | Expected result | Ref | Sev | Result | Evidence link | Tester | Date | Notes
DO-01 | CI gate blocks bad PR | Open a PR with a seeded lint or test failure | Merge blocked until fixed | 08 s6 | C | Blocked | QA-Evidence/DO-01/ | Claude Code (automated pre-audit) | 2026-08-21 | Split verdict folded per instruction, strictest reading. PROVEN locally: .github/workflows/ci.yml exists with all five steps (typecheck, lint, unit tests, claims gate, build); seeded lint error on temp branch qa/do01-lint-seed made pnpm lint exit 1 (archived), clean tree passes lint + 25/25 vitest tests, typecheck/claims/build pass per CA-02/CA-10 and the running production build; checkout restored. NOT verifiable here: GitHub-side enforcement (branch protection/required checks on main) - gh CLI absent and REST returns 403 (no GitHub App access in session); origin main is still at the initial commit with work unmerged on a feature branch, so no PR has exercised the gate. Also noted: docs/07 T0.4's Playwright shell, axe and Lighthouse CI steps are absent from ci.yml, with an in-file deferral comment tracking them to E5/E6.
DO-02 | Staging auto-deploy | Merge to main; watch Action | Builds on server, health check passes, symlink flips | 08 s6 | M | Blocked | QA-Evidence/DO-02/ | Claude Code (automated pre-audit) | 2026-08-21 | No live Actions run history available pre-staging. Pre-check: ci.yml exists, triggers on PR + push to main, runs typecheck/lint/unit/check:claims/build per docs/08 s6. Deviation: axe and Lighthouse CI budget steps NOT present — YAML documents deferral until a preview environment exists (docs/07 E5/E6). Branch protection (merge blocked on red) not verifiable from the clone.
DO-03 | Production approval deploy | Tag v-test with approval step | Deploys only after manual approval | 08 s6 | M | Blocked | QA-Evidence/DO-03/ | Claude Code (automated pre-audit) | 2026-08-21 | Inert until HOSTPOINT_* secrets exist (workflow self-skips). Pre-check vs docs/08 s6: deploy-staging.yml matches the prescribed flow (SSH deploy key, releases/<sha> worktree, on-server pnpm install+build for FreeBSD natives, health-check 3002, symlink flip, supervisorctl restart) with two deviations: no Payload-migrations step (E2 not built) and the health check is 'curl ... ¦¦ true' so a failing check does NOT abort before the symlink flip — weaker than spec intent.
DO-04 | Rollback drill | Repoint symlink to previous release | Site restored under 5 minutes; documented | 08 s6 | C | Blocked | QA-Evidence/DO-04/ | Claude Code (automated pre-audit) | 2026-08-21 | Requires Hostpoint pipeline. Pre-check note: no production deploy workflow file (tag v* + manual approval per docs/08 s6) exists yet in .github/workflows/ — open build item.
DO-05 | Process resilience | Kill the node process; reboot server in window | supervisord restarts; autostart after reboot | 08 s2 | M | Blocked | QA-Evidence/DO-05/ | Claude Code (automated pre-audit) | 2026-08-21 | Rollback drill needs the server's releases/current symlink layout; no server pre-staging.
DO-06 | Log rotation | Inspect CSC logs | Rotating per config | 08 s2 | Mn | Blocked | QA-Evidence/DO-06/ | Claude Code (automated pre-audit) | 2026-08-21 | Custom Service Control/supervisord restart-survival (docs/08 s2, spike S0 step 4) requires the Hostpoint server.
DO-07 | Alerting works | Stop the service briefly | Uptime alert received by owners | 07 T7.5 | M | Blocked | QA-Evidence/DO-07/ | Claude Code (automated pre-audit) | 2026-08-21 | Monitoring/alerting requires the host. Local pre-check: GET /api/health returns 200 JSON on the QA server.
DO-08 | DNS and SSL review | Panel review: records, HSTS, redirects, www policy | Per docs 06 s5 and 08 s3 | 08 s3 | M | Blocked | QA-Evidence/DO-08/ | Claude Code (automated pre-audit) | 2026-08-21 | DNS cutover/domain wiring (apex, www 301, staging subdomain per docs/08 s3) requires the Hostpoint Control Panel and DNS zone; none exist.
DO-09 | Staging protected | Open staging logged out | Password prompt; robots disallow | 08 s3 | C | Blocked | QA-Evidence/DO-09/ | Claude Code (automated pre-audit) | 2026-08-21 | Staging host does not exist, but staging-mode robots behaviour verified on this server (NEXT_PUBLIC_ENV unset = staging semantics): GET /robots.txt returns 'User-Agent: * / Disallow: /' (HTTP 200). Remaining scope (basic auth on staging.skaahhospitality.com, prod robots allow) is server-side.

## 11-Launch-Gate
SoW 13 criterion | Evidence source | Status | Sign-off
1. All 27 pages plus legal complete in English; zero TO CONFIRM in production | Sheets 1, 2 | NOT MET: all 27 pages complete and copy-faithful (CC-01 Pass) but 78 [TO CONFIRM] markers open; production build correctly blocked by the claims gate (CA-11).
2. Every enquiry segment tested end to end incl. attachments, mail, payload, sheet, flags | Sheet 3 | PARTIALLY MET: all six segments pass end to end at API and UI level incl. 95 MB upload, sniffing, flags, payload schema (FE-01 to FE-16, FE-19); mailbox, acknowledgement and sheet delivery Blocked pending Hostpoint (FE-17/18/20).
3. Core Web Vitals pass with film enabled; WCAG 2.2 AA with no critical issues | Sheets 5, 6 | PARTIALLY MET after round 2: axe zero critical AND zero colour-contrast nodes across templates (AC-01/AC-05); CLS now 0 on all five audited templates (PF-05 fixed); lab LCP 3.0 s vs 2.0 s budget remains on 4 routes pending the designed poster LCP element (PF-01 to 04); screen-reader passes pending human audit.
4. Structured data error-free; 301 redirects live; sitemap and robots correct | Sheet 4 | PARTIALLY MET: JSON-LD structurally valid, 137 blocks, zero errors (SS-05); sitemap and robots correct (SS-03/04); app-level redirects live (SS-07); legacy skaah.com 301s pending Hostpoint DNS.
5. Analytics and consent verified for all segments and tap events | Sheet 4 | PARTIALLY MET after round 2: consent gating proven (SS-14); 11 of 13 events now wired incl. article_read and phone_click (SS-13 fixed), film events await the film; live firing awaits the Plausible domain.
6. Cross-browser and device matrix executed and documented | Sheet 8 | PARTIALLY MET: Chromium desktop, emulated Android and 360/768/1440 widths pass with full journeys (CM-01/06/08/09/10); Safari, Firefox, Edge, iOS and iPad Blocked pre-staging (CM-02 to 05, 07).
7. Content approved by the CEO; naming permissions checklist complete or fallback live | Sheet 2 + consent file | PENDING: fallback copy live everywhere with zero named states (CC-02/03/04 Pass); CEO content approval, the consent checklist and the human hero read test (CC-14) outstanding.
8. Editor trained; documentation and export demonstrated; accounts SKAAH-owned | Sheets 9, 1, 10 | NOT MET: CMS not embedded so editor tasks are Blocked (sheet 9); export runs but is incomplete (CA-12 defect); training and account handover pending.
Severity rule: Critical and Major block launch. Minor issues may launch only if logged with owner and a 30 day fix date, approved by the CEO with CTO sign-off.
Sign-off
Role and name | Signature / initials | Date | Decision
First-line QA: Ms. Revathi Meegada
Technical and code audit: Mr. Hanuma Kuna, CTO
Functional review: Mr. Varaprasad
Final decision: Mr. Amar Kavi, CEO
Final decision (CEO): Ready / Ready with logged minors / Not ready